## Kids Camp Products
Kids Camp Products | Date Requested | Jan. 14.2021 |  | TW task request | Click Here | Deadline | Feb-June 2021 | Updated 2022
Promo Products | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs | 2022 Updates
[8 empty] | Date delivered | Price update
Announcement slide |  | Click Here | Jan. 21.21 | 2 weeks | 0 | 0 | 1920x1080 | Dec. 2. 22 | NA
Email Graphic |  | Click Here | Feb. 22.21 | 2 weeks | 0 | 0 | 600x156 | Jan. 26.22 | NA
1250x800
Web Graphics |  | Click Here | Established 2020 | Reused | 0 | 0 | 2560x600
600x400
Invite Post Card |  | Click Here | Feb. 8. 21 | 3 weeks | QTY=2500 | 452 | 4x6 14pt uncoated cover | Dec. 16. 21 | 452
HOT Graphics
Family Night Post Card |  | Click Here | Feb 11.21 | 3 weeks | QTY=2500 | 112 | 4x6 14pt uncoated cover | Jan. 19.22 | 98
Gotprint
Rock Banner |  | Click Here | Jan. 31.21 | 3 weeks | NA | 0
Event Products
Aframe (dated) |  | Click Here | May 20.21 | 4 weeks | Check-in QTY=6 | 648 | 24x36 coraplast
HOT Graphics |  |  |  |  | Pick up QTY=6 | ($36 ea)
Medical QTY=6
Total= QTY=18
Tent Signage |  | Click Here | Jan. 12.22 | 2weeks | Kids QTY=12 | 563 | 16x28
HOT Graphics |  |  |  |  | Check in=12 | ($23 ea) | Single Sided Adhesive Vinyl,
[5 empty] | Total=QTY=24 |  | Made From 3m Controltac 40C-114 Clear
Masks |  | Click Here | May.25.21 | 4 weeks | Adult QTY=100 | 519
4Imprint |  |  |  |  | Kids QTY=400 | 1104
POP signs |  | Click Here | June. 13.21 | 2 weeks | QTY=6 of each sign | 404 | 20x20 White 3mm PVC
CGS imaging |  |  |  |  | 1st=6 | ($13.47 ea)
2nd=6
3rd=6
4th=6
5th=6
Total=QTY=30
Flag |  | Click Here | June. 20.21 | 2 weeks |  |  |  | REORDERED
CGS Imaging |  |  |  | CGS Imaging | QTY=6 Welcome | 1536 | 6.5’ flag (no hardware included)
[5 empty] | QTY=6 Kids Camp | ($128 ea)
Amazon |  |  |  | Amazon | QTY=12 Poles | 384 | Pole/Stake |  | 576
Vinyl Floor Banner |  | Click Here | May .15.22 | 20 weeks | Waiting on Vendor | 2374 | 31x90 double sided
[5 empty] | QTY=1 for Each Campus | ($396 ea)
Displays2go
Photo Backdrop |  | Optional | NA | 2 weeks | QTY=1-4 | 308 | 120x96 Photo Display Fabric
CGS Imaging
QR Code Poster |  | Click Here | Apr.29.21 | 2 weeks | PB=6 | 728
HOT |  |  |  |  | FN=4 | ($28 ea)
OR=4
ST=4
WH=4
WT=4
Total QTY=26
Check-in Central |  | Optional | NA | 2-3 weeks | On hand
HOT graphics |  |  |  |  | QTY=2 | 36 | 13mm Scrim
Displays2go |  |  |  |  | QTY=2 | 19 | Hardware
Room Signs |  |  |  |  | On hand | 0 | Tyvek
In house print/HOT graphics |  |  |  |  | 1 of each
2021 In house print
[5 empty] | If need replaced |  | 8.35x11
will need Quote
Parent Pick-up Sign |  | Click Here | May 11.21 | 2 weeks | FN=QTY100 | In house print | 8.5x11
[5 empty] | OR=QTY=100 | 0
PB=QTY=400
Total QTY=600
Dreamteam T-shirt |  | Click Here | June. 13. 21 | 2 weeks | 50-S | 2270
Jupmode |  |  |  |  | 75-M
75-L
50-XL
25-2X
10-3X
8-4X
Total=293
Youth Baptism Shirt |  | Click Here | June. 13. 21 | 2 weeks | 25-S | 1051
Jupmode |  |  |  |  | 45-M
45-L
20-XL
15-2 X
Total=150
Lanyards |  | Click Here | June. 13. 21 | 3 weeks | Safety-50 | 735
Access Event Solutions |  |  |  |  | Medical-15
Door Holder-40
Social media-5
Production-25
Band-25
Media-25
Host-6
Activities-25
Group leader-250
Ministry Director-4
Service programming-4
Op Director-4
Speaker-3
Prayer team-25
Blank-100
Total=591
Maps |  | Click Here | Mar. 30.21 | 3 weeks | On file | 0
FN Parent Map
FN Dreamteam Map
OR Parent Map
OR Dreamteam Map
WT Parent Map
WT Dreamteam Map
Kids Camp Guide |  | Click Here | Mar. 10. 21 | 3 weeks | On file | 0 |  | Jan. 31.22 | NA
FAQ |  | Click Here | Mar. 15. 21 | 3 weeks | On file | 0
[5 empty] | Parent version |  |  | Jan. 22.22 | NA
[5 empty] | Dreamteam version |  |  | Mar.22.22 | NA
Videos |  | Click Here |  |  | On file | 0
|  |  | Apr. 19.21 |  | DreamTeam Video |  |  | Feb. 16.22 | NA
|  |  | Mar. 4. 21 |  | Parent Video
|  |  | Jun. 25. 21 |  | Recap
[5 empty] | Promo |  |  | Dec. 8. 22 | NA

## Kids Camp Marketing
Kids Camp Marketing 2021 | Date Requested | Nov. 19,2020 | Kids Camp Marketing 2022 | Date Requested | Dec. 20.21
Email | Dates | TW Task Click Here
Family ministry email | Mar. 5. 21 | See TW Calendar
In-Active families | Mar. 9.21
Active families | Mar. 9.21
P.S. All Actives | Mar. 25.21
Family ministry email | Apr. 2.21
P.S. All Actives | Apr. 8.21
In-Active families | Apr. 27.21
Active families | Apr. 27.21
P.S. All Actives | May 6.21
Family ministry email | May 7. 21
In-Active families | May 25.21
Active families | May 25.21
Vision Cast | June 7. 21
Social | Date | TW Task Click Here | Social | Date | TW Task Click Here
March 7 First Announcement (Kids + Visioncast) | Mar.7. 21 | HERE | Leading Up (Promotions photos, quotes, teasers, informations) |  | HERE
March 15 Confetti kids photos + invite and parent quote (post on main, re-share to Kids) | Mar.15.21 |  | Registration | Jan.-Apr.22
March 22 Confetti kids photos + invite and parent quote (post on Kids, re-share to main) | Mar. 22.21 |  |  | Feb. 1.22
March 29 Confetti kids photos + invite and parent quote (post on Kids, re-share to main story) | Mar. 29.21 |  |  | Feb.8.22
April 5 Spotify playlist share (Kids) + add to linktree / link in bio (Kids) | Apr. 5. 21 |  |  | Feb. 15.22
April 12 My name is _____, I'm ___ years old and I can't wait for camp! (Main, re-share to Kids) | Apr. 12.21 |  |  | Feb. 22.22
April 19 Photos of Kids in new Kids space (Kids) | Apr.19.21 |  |  | Mar. 1. 22
April 26 Quote about Kids Camp from Kids Directors at Findlay (Kids) | Apr. 26.21 |  |  | Mar. 8. 22
May 3 Quote about Kids Camp from Kids Directors at Oregon (Kids) | May.3.21 |  |  | Mar. 15. 22
May 10 Quote about Kids Camp from Kids Directors at Perrysburg (Kids) | May10.21 |  |  | Mar. 22.22
May 17 Quote from parent excited for Kids Camp (Kids) | May17.21 |  |  | Mar. 29.22
May 24 Quote from parent excited for Kids Camp (Kids) | May 24.21 |  |  | Apr. 5. 22
May 27 Quote from parent excited for Kids Camp (Kids) | May 27.21 |  |  | Apr. 12.22
May 30 Tomorrow is deadline to register (post on, re-share to Kids) | May 30.21 |  | Only a few more weeks until price change | Apr. 19.22
May 31 Deadline to register ($15 per kid) | May 31.21 |  | Final Before price change | Apr. 26.22
Jun 7 Feature dances happening at Kids Camp (Kids) | Jun.7.21 |  | Late Registration $30 | May 3.22
Jun 14 Feature dances happening at Kids Camp (Kids) | Jun. 14. 21 |  |  | May 10.22
Jun 21 BTS coverage (Post to Kids, re-share to main) | Jun. 21.21 |  |  | May 17.22
June 22 Event coverage (Post to main, re-share to Kids) | Jun. 22.21
June 23 Event coverage (Kids) | Jun. 23.21
June 24 Event coverage (Kids) | Jun. 24.21
June 27 Kids Camp Recap (Post to main, re-share to Kids) | Jun. 27.21
At Camp Strategy
Week before camp
Day before camp
Day 1 of Camp
Day 2 of Camp
Day 3 of Camp
WEB | Date | TW Task Click Here | WEB | Date | TW Task Click Here
Webpage updated | Mar. 16.21 | HERE | Webpage updated | Dec. 14. 21 | HERE
PROGRAMMING | 2021 |  | PROGRAMMING | 2022
Schedule Film and Photography team | Jun. 14.21 | HERE | Schedule Film and Photography team
Creative Concepts | Apr. 25-May 10.21 |  | Creative Concepts
Wow Meeting | May 10.21 |  | Wow Meeting | Apr. 21.22
Pitch: No info in TW |  |  | Pitch | May 5. 22
How Meeting: No info in TW |  |  | How Meeting: No info in TW | May 19.22
Schedule bands: May 19 | May 19.21 |  | Schedule bands
Schedule Central Production: May 5 | May 5.21 |  | Schedule Central Production
LED background | Jun.8.21 | HERE | LED background
Session Programming | May 19-Jun. 24.21 | HERE | Session Programming |  | HERE
o Tues Session |  |  | o Tues Session
o Wed Session |  |  | o Wed Session
o Thurs. Session |  |  | o Thurs. Session
o Family Night Session |  |  | o Family Night Session
o Recap video |  | Dropbox Here | o Recap video

## Fusion Camp Products
Fusion Camp Products | Date Requested | Jan. 14.21 |  | TW task request | Click Here | Deadline | June 5/6.21 | Updated 2022
Promo Products |  |  |  |  | Click Here |  |  | 2022 Updates
Name | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs | Date delivered | Price update
Announcement slide |  | Click Here | Feb. 25.21 | 4 weeks | 0 | 0 | 1920x1080 | Nov.15.21 | Fusion Camp
[8 empty] | Dec.6.21 | Camps
Email Graphic |  | Click Here | Nov. 11.20 | 2 weeks | 0 | 0 | 600x156
|  |  |  | Reused |  |  | 1250x800
|  | Click Here | Sept. 15.21 | 3 weeks | 0 |  | 1920x1080 | Dec. 6. 21 | NA
1080x1080
Web Graphic |  | Click Here | Apr. 20.21 | 2 weeks | 0 |  | 2560x600
600x400
Video | DreamTeam | Click Here | May 3. 21 | 12 weeks | 0
Parent
Recap
Post Cards |  |  | June 18.2019 | 4 weeks | Invite PC QTY=2500 | 104 | 100#Uncoated cover | Dec. 6.21 | 207
Gotprint |  |  | Mar. 5. 2020 |  | Special PC 4camp QTY=500 | 55 | 4x6 2 sided
QR Code Banner |  | Click Here | April.27.21 | 1 week | QTY=6 | $28 ea. | 18x24 Coraplast sign | Feb. 17.22 | 270
HOT graphics | [7 empty] | QTY=12 2 per campus
Questions about Fusion Camp Sign |  | Click Here | Feb. 18.21 | 1 week | Campus (Acrylic) | 0 | 8.5x11
In house print
Camp Roadside Banner |  | Click Here | Mar. 14.22 | 2 weeks | QTY=5 | 226
CGS imaging |  |  |  |  | OR=2
ST=2
WT=1
Camp Promo Shirt |  | Click Here |  |  | QTY=60 | 682 | White T-shirt Teal and Lime imprint ink
[5 empty] | S=8 | $11 ea
M=20
L=15
XL=15
2X=1
3X=1
Event Products
Camp Swag |  | Click Here |  | 4 weeks
Water Bottle: 4 Imprint |  |  |  | 4 weeks | QTY=100 | 309 ($3.09 ea) | Clear Impact Halcyon Water Bottle with Flip Straw - 24 oz.
T-shirts: Jupmode |  |  |  | 2 weeks | Purple |  | Triblend t-shirt
3-S
1-L
2-XL
1-2X
1-3X
Teal
2-S
7-M
5-L
4-XL
Red
8-M
2-L
4-XL
1-2X
[5 empty] | Total QTY=39 | $589 ($15 ea)
Camps Vinyl Floor banner |  | Click Here | May .15.22 | 20 weeks | Waiting on Vendor | 2374 | 31x90 double sided
Displays 2 go |  |  |  |  | QTY=1 for Each Campus | ($396 ea)
Room Signs |  | Click Here | Feb 18.20 | 4weeks | Girl/Boy QTY=4 signs | 0 | 8.5x11 Digital 28#paper
In house print |  |  |  |  | Safety QTY= 3 signs | 0
[5 empty] | Care Sign | 0
[5 empty] | Question about Fusion Camp | 0
[5 empty] | Emergency Reference | 0
Signs |  | Click Here | Feb. 1. 21 | 1 week | 8.5x11 Landscape QTY=?? | 0
In house print
|  | Click Here | Jan.30.20 | 1 week | 8.5x11 Portrait QTY=?? | 0
Emergency Chart |  | Click Here | April. 21.21 | 2 weeks | QTY=5 | 205 | 8.5x11 80# cover
HOT Graphics |  |  |  |  | QTY=10 | 215
Camp Binder Covers |  | Click Here | July 26.10 | 2 weeks | Ministry Coordinator | 0 | 8.5x11 80# cover
In house Print |  |  | Reused |  | Activities Coordinator
Groups Coordinator
Operarations Coordinator
Medical Coordinator
Safety Coordinator
Door Holder Coordinator
Check-in Coordinator
Serve Programming Coordinator
Music Coordinator
Production Coordinator
Media Coordinator
Booklet Cover |  | Click Here | June. 14.21 | 4 weeks | QTY=650 | 330 | 100#uncoated cover
HOT Graphics |  |  |  | QUOTE | QTY=650 | 935 | 100# unc. cover over 70# unc. text, cover 4 color, text black 2S, 5.5x8.5
36 PageCover
Fusion Camp Brochure |  | Click Here | June.18.19 | 2 weeks | QTY=2500 | 751 | 80# uncoated cover 8.5x11
HOT Graphics
Fusion Camp Maps |  | Click Here | Feb.20-June 21 | 2 weeks | Deployment | 0 |  | Dec. 6.21 | NA
In house print |  |  |  |  | Door Holder
Lost Student
Parents
Dreamteam
Medical
Lanyards |  | Click Here | July 8,20 |  | Prayer Team=15 | 412 | Matrix Laminates
Access Event Solutions |  |  |  |  | Medical-5
Door Holder-10
Media-4
Production-12
|  | Click Here | Sept. 8.19 | QTY=50 | Band-10 | 152
Safety-6
Host-2
Activities-6
Group leader-100
Ministry Director-1
Service programming-1
Op Director-1
Speaker-7
Group Coach-11
Groups Coordinator-1
Activities Coordinator-1
Prayer team-15
Blank-37
Total=230
Checkin/Check out Signs |  | Click Here | Mar. 18.22 | ?? |  |  |  | Ready to order
Aframe Signs |  | Click Here | May 5.20 | 1 week | West Campus | $36ea | 24x36 Coraplast One sided
HOT Graphics |  |  |  |  | East Campus
Late/Midweek check in Pull Forward
Late/Midweek Check in Wait/Call
|  | Click Here |  |  | Added Operational Parking |  |  | Ready to order
[5 empty] | Added Late Arrive left arrow |  |  | Ready to order
Pop Signs |  | Click Here | Feb.25.20 | 2 weeks | Cabin Colors | $13.46 ea | 3mil PVC 20x20
CGS imaging |  |  |  |  | Best is Yet to Come | QTY=11
Follow on SM
[5 empty] | Ask me how I can help | $12 ea | 3 mil PVC 36x10
[5 empty] | You made it/Have a Great Week | QTY=4
Student Mask |  | Click Here | Jun. 20.21 | 4 weeks | QTY=100 | 527 | Double ply
4 Imprint
Drawstring Bag |  | Click Here | Apr. 21.22 | 4 weeks | QTY=650 | 943
4 Imprint
Key Chain |  | Click Here | May 25. 21 | 4 weeks | QTY=125 | 342
4 Imprint
Sticker |  | Click Here | Mar.5.20 | 4 weeks | QTY=500 | 141
Care Backdrop |  | Click Here | Feb. 2. 21 | 2 weeks | QTY=1 | $308 ea.
CGS Imaging
FAQ |  | Click Here | Jul.15.20 | 2 weeks | Info Doc | 0 |  | Dec. 6. 21 | NA
In house print |  |  |  |  | Dreamteam Info Doc.
Camp Guide |  | Click Here | Dec. 10.21 | 2 weeks | QTY=?? | 0 | 8.5x11 Digital | Mar. 23.22 | NA
Fusion Camp Apparel |  | Click Here | May. 29.20 | 2 weeks | Leader Tshirt | 914 | Triblend
20-S
55-M
35-M
XL-10
[5 empty] | Staff | 608
15-S
25-M
20-L
20-XL
2-2X
1-3X
1-4X
[5 empty] | Production | 442
5-S
10-M
10-L
5-XL
5-2X
[5 empty] | Safety | 117
2-L
2-XL
4-2X
[5 empty] | Medical | 157
2-S
2-M
4-L
2-XL
[5 empty] | Students | 4004
240-S
125-M
75-L
25-XL
5-2X
[5 empty] | 2nd order | 209
Leader
1-XL
3-2X
2-4X
Staff 1-2X
Production
1-2X
Medical 2-S
[5 empty] | Overall Total | 6451
Student blanket |  | Click Here | Feb. 25.22 | 4 weeks
Jupmode |  |  |  |  | QTY=20 Embroidery | 350
Amazon |  |  |  |  | QTY=20 Fleece blanket | 246
[5 empty] | Total= | 596
$30 ea
Laundry Bags |  | Click Here | Feb. 21. 22 | 4 weeks | QTY=200 | 693 | Black Mesh Laundry Bag (white imprint ink)
Proimprint

## Fusion Camp Marketing
Fusion Camp Marketing 2021 | Date Requested | Jan. 14,2021 | Fusion Camp Marketing 2022 | Date Requested | Dec. 20.21
Email | Dates | TW Task Click Here | Email | Dates | TW Task Click Here
Family ministry email | Mar. 5. 21 | See TW Calendar | Fusion Camp invite | Nov.30.21 | HERE
Family ministry email | Apr. 2.21 |  | Registration Open Email | Dec.3.21
Family ministry email | May 7. 21 |  | Christmas Camp Promo Email | Dec. 23. 21
Family ministry email:Registration Deadline | May 31.21 |  | New Years Camp Promo Email | Jan. 5. 22
Family ministry email | July 2.21 |  | Passion Promo Email | Feb. 28.22
|  |  | Registration Price Break | Apr. 25. 22
Social | Date | TW Task Click Here | Registration Deadline | May 23. 22
Driven by Student Directors |  |  | Social | Date | TW Task Click Here
Driven by Student Directors
WEB | Date | TW Task Click Here
Reviewed to see what changes were needed | July 7.20 | HERE | WEB | Date | TW Task Click Here
Completed updates | July 14.20 |  | Webpage updated | Jan. 20.22 | HERE
Updated Registration deadline | May 4. 21
PROGRAMMING | 2021
Schedule Film and Photography team | Jun. 14.21 | HERE | PROGRAMMING | 2022
Creative Concepts | Mar. 4. 21 |  | Schedule Film and Photography team | ?
Wow Meeting: No info in TW |  |  | Creative Concepts | Feb. 2.22 | HERE
Pitch: No info in TW |  |  | Wow Meeting | May 5. 22 | HERE
How Meeting | May 24.21 |  | Pitch | Jun.5.22
Speakers Locked | April. 15 |  | How Meeting: No info in TW | June. 9.22
Message Background | June 28.21 |  | Schedule bands | ?
Session Programming |  |  | Schedule Central Production | ?
o Monday Session |  |  | Message Slides | May 17.22
o Tues AM Session |  |  | Session Programming
o Tues PM Session |  |  | o Monday Session
o Wed AM Session |  |  | o Tues AM Session
o Wed PM Session |  |  | o Tues PM Session
o Thurs. AM Session |  |  | o Wed AM Session
o Thurs. PM Session |  |  | o Wed PM Session
o Recap video |  | Dropbox Here | o Thurs. AM Session
o Thurs. PM Session
o Recap video

## High School Camp Products
High School Camp Products | Date Requested | Nov. 7.21 |  | TW task request | Click Here | Deadline | Jun. 5/6 | Updated 2022
Promo Products | [7 empty] | 2022 Updates
Name | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs | Date delivered | Price update
Postcard |  | Click Here | Dec. 22.21 | 2 weeks | 2500 | 104 | 4x6 14pt uncoated cover | Dec. 22.21 | 104
Gotprint
Announcement slide |  | Click Here | Jan. 20.21 | 2 weeks | 0 | 0 | 1920x1080 | Nov. 11. 21 | 0
Nov. 11.21
Social Media Graphics |  | Click Here | Jan. 20.21 | Reused | 0 | 0 | 1920x1080 |  | 0
1080x1080
Email Graphic |  | Click Here | Feb. 17.21 | 4 weeks | 0 | 0 | 600x156
1250x800
Rock Graphics |  | Click Here | Jan. 20.21 | 2 weeks | 0 | 0 | 1140x156
1250x800
Web |  | Click Here | Feb. 4. 21 | 2 weeks | 0 |  | 2560x600
600x400
QR Code Banner |  | Click Here | April.27.21 | 1 week | QTY=6 | $28 ea. | 18x24 Coraplast sign | Feb. 17.22
HOT graphics | [7 empty] | QTY=12 2 per campus
Camps Vinyl Floor banner |  | Click Here | May .15.22 | 20 weeks | Waiting on Vendor | 2374 | 31x90 double sided
Displays 2 go |  |  |  |  | QTY=1 for Each Campus | ($396 ea)
Video |  | Click Here | Feb.12.21 |  | Parent | 0 |  | Nov. 23. 21 | 0
Promo
Event Products
Luggage Tag |  | Click Here | Dec. 1.20 | 4 weeks | QTY=150 | 397 | 4x3 baggage tag
Sun Solutions
Student Mask |  | Click Here | Jun. 20.21 | 4 weeks | QTY=100 | 527 | Double ply
4 Imprint
Ready to Order
Aframe Signs |  | Click Here | May 5.20 | 1 week | West Campus | $36ea | 24x36 Coraplast One sided
HOT Graphics |  |  |  |  | East Campus
Late/Midweek check in Pull Forward
Late/Midweek Check in Wait/Call
Added Operational Parking
Added Late Arrive left arrow
Drawstring Bag |  | Click Here | Jun. 9.21 | 4 weeks | QTY=150 | 602 | Galaxy Sportsack
4 Imprint
Booklet Cover |  | Click Here | June. 14.21 | 4 weeks | QTY=200 | 172 | 100#uncoated cover
HOT Graphics |  |  |  | QUOTE | QTY=200 | 478 | 100# unc. cover over 70# unc. text, cover 4 color, text black 2S, 5.5x8.5
36 PageCover
Info Sheet |  | Click Here | Feb. 1. 21 | 2 weeks | QTY=? | 0 | 8.5x11 Digital 28# Paper | Nov. 29.21 | NA
Camp Maps |  | Click Here | Feb.20-June 21 | 2 weeks | Deployment | 0 |  | Dec. 6.21 | NA
In house print |  |  |  |  | Door Holder
Lost Student
Parents
Dreamteam
Medical
Camp Guide |  | Click Here | Dec. 10.21 | 2 weeks | QTY=?? | 0 | 8.5x11 Digital | Mar. 23.22 | NA
Photo Back drop |  | Click Here |  | 2 weeks | QTY=1 | $308 ea.
CGS Imaging
Pop Signs |  | Click Here | Apr. 12. 21 | 2 weeks | Version 1=QTY=2 | 162 | 3mil PVC
CGS Imaging |  |  |  |  | Version 2=QTY2 |  | 20x20
Version 3=QTY=2
Version 4=QTY=2
Version 5=QTY=1
Version 6=QTY=2
Version 7=QTY=2
TOTAL=13
Room Signs |  | Click Here | Feb 18.20 | 4weeks | Girl/Boy QTY=4 signs | 0 | 8.5x11 Digital 28#paper
In house print |  |  |  |  | Safety QTY= 3 signs | 0
[5 empty] | Care Sign | 0
[5 empty] | Question about Fusion Camp | 0
[5 empty] | Emergency Reference | 0
Key Chain |  | Click Here | May 25. 21 | 4 weeks | QTY=125 | 342
4 Imprint
Student Shirt |  | Click Here | Jun. 23. 21 | 2 weeks | Tank | 913 | Dark Grey Tank White imprint ink
Small: 30
Medium: 55
[5 empty] | Large: 40 |  |  | Dec. 6.21 | NA
X-Large: 10
2X:8
4X:1
Total=144
Lanyards |  | Click Here | Jun. 11.21 | 3 weeks | Ministry Director-1 | 289 | Matrix Laminates
Access Event Solutions |  |  |  |  | Group Coordinator-1
Group Coach-11
Activities Coordinator -1
Host-2
|  | Click Here | Sept. 8.19 | QTY=50 | Service programming director-1 | ??
Media-2
Production-6
Medical-2
Band-6
Production-6
Medical-2
Safety-2
Speaker-4
Operation Director-1
Door Holder -5
Blank-12
Total=100
Ready to order
Emergency Chart |  | Click Here | April. 21.21 | 2 weeks | QTY=5 | 205 | 8.5x11 80# cover
HOT Graphics |  |  |  |  | QTY=10 | 215
Ready to order
Ready to order
[8 empty] | Dec. 6. 21 | NA
[8 empty] | Mar. 23.22 | NA

## High School Camp Marketing
High School Camp Marketing 2021 | Date Requested | Jan. 14,2021 | High School Camp Marketing 2022 | Date Requested | Dec. 20.21
Email | Dates | TW Task Click Here | Email | Dates | TW Task Click Here
Family ministry email | Mar. 5. 21 | See TW Calendar | High School Camp invite | Nov.30.21 | HERE
Family ministry email | Apr. 2.21 |  | Registration Open Email | Dec.3.21
Family ministry email | May 7. 21 |  | Christmas Camp Promo Email | Dec. 23. 21
Family ministry email:Registration Deadline | May 31.21 |  | New Years Camp Promo Email | Jan. 5. 22
Family ministry email | July 2.21 |  | Passion Promo Email | Feb. 28.22
|  |  | Registration Price Break | Apr. 25. 22
Social | Date | TW Task Click Here | Registration Deadline | May 23. 22
Driven by Student Directors |  |  | Social | Date | TW Task Click Here
Driven by Student Directors
WEB | Date | TW Task Click Here
Registration info Update | Feb.10.21 | HERE | WEB | Date | TW Task Click Here
Webpage Updated | Mar. 9.21 | HERE | Reviewed to see what changes were needed | Nov. 10.21 | HERE
Remove Pricing | Apr. 1. 2021 | HERE | Completed updates | Jan. 19.22
PROGRAMMING | 2021 |  | PROGRAMMING | 2022
Schedule Film and Photography team | Jun. 14.21 | HERE | Schedule Film and Photography team | ?
Creative Concepts | Mar. 4. 21 |  | Creative Concepts | Feb. 2.22 | HERE
Wow Meeting | Mar. 31 |  | Wow Meeting | May 11. 22 | HERE
Pitch: No info in TW |  |  | Pitch | May 25.22
How Meeting: No info in TW |  |  | How Meeting | June. 1.22
Speakers Locked |  |  | Schedule bands | May 2. 22
Message Background | June 28.21 |  | Schedule Central Production | ?
Session Programming |  |  | Message Slides | May 17.22
o Friday PM Session |  |  | Session Programming
o Saturday AM Session |  |  | o Friday PM Session
o Saturday PM Session |  |  | o Saturday AM Session
o Saturday PM Session