## DTCelebration Products22
Dreamteam Celebration Products 2022 | Date Requested | Jan. 18.2022 |  | TW task request | Click Here | Deadline | Mar. 23. 2022 Event date
Promo Products | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs
Email Graphic |  | Click Here | Jul.21.21 | Reused | na | na | 1250x800
Social Media Graphic | [6 empty] | 1920x1080
Web Graphics |  | Click Here | Feb. 21.22 | Reused | na | na | 2560x600
600x400
Postcard |  | Click Here | Mar. 3. 22 | 4 weeks | 1000 | 58 | 4x6
QR Code Poster |  | Click Here | Mar. 3. 22 | 1 week | QTY=12 | 395 | 18x24 coraplast
HOT graphics |  |  |  |  | 2 per campus
[5 empty] | QTY=8 |  | 8.5x11 styrene sign with kick stand
1 per campus
Invite Video |  | Click Here | Feb. 25. 22 | 3 weeks | na | na
Recap Video |  | Click Here | Mar. 30.22 | 4 weeks | na | na
Event Products
Aframe |  | Click Here | Nov. 3.21 | Optional |  | $236ea | 24x36 coraplast
HOT Graphics
POP signs |  | Click Here | Sept. 1. 21 | Reused | 0 requested | 13 | 20x20 White 3mm PVC
CGS imaging |  |  |  |  | On hand Sept.2021
FN=2
OR=2
PB=2
ST=2
WT=2
W=2
QTY=12
Flag |  | Click Here | Option | 2 weeks | 0 requested | 135
CGS Imaging |  |  |  | CGS Imaging |  | 48 | 6.5’Staked flag (no hardware included)
Amazon |  |  |  | Amazon |  |  | Stake
Vinyl Floor Banner |  | Click Here | Oct. 14.21 | Reused | 0 requested | 396 | 31x90 double sided
Displays2go |  |  |  |  | On hand Oct. 21
QTY=2
Check in Sign |  | Click Here | Nov. 11.21 | Resused | QTY=1-4 | 108 | Double sided
HOT Graphics |  |  |  |  | QTY=1-15 | 15 | 13mm scrim
Displays2go | [6 empty] | Hardware
[5 empty] | QTY=2 | 72 | 36x72SG
HOT Graphics | [6 empty] | 24x18 checkin
Photo Back drop |  | Click Here | Dec. 3. 2021 | Resused | On hand Dec. 21 | 308 | 120x96
CGS imaging |  |  |  |  | QTY=1
Swag
Ministry ordered Candles |  | Click Here | Jan.27.22 | Ministry ordered | ?? | ?? | ??
Candle label artwork
Stanchion Signs |  | Click Here | Mar. 14.22 | 2 weeks. | QTY 3 Each | 0 | 8.5x11
In house print |  |  |  |  | Arts
Family
Next Steps
Programming | Requested Feb. 6. 2022
Wow |  | TW link | Jan. 27-Feb. 1
LC identified Jan. 27
Pitch |  |  | Feb. 14
How |  |  | No notes
Service Plan |  |  | Delivery Dates
Pre and Post Slides |  |  | Mar. 22.22
Opening Song |  |  | Mar. 9.22
Welcome |  |  | Mar. 21.22
Ministry Mishaps |  |  | Mar. 20.22
Host Vision |  |  | Mar. 22.22
LC |  |  | Mar. 22.22
Message Slides |  |  | Mar. 21.22
Worship Set |  |  | Mar. 15.22
Send off |  |  | Mar. 21.22

## DTCelebration Marketing22
Email-Event Mar. 23. 22 | Date Requested | Jan. 18.2022
Email- | Dates | TW Task Click Here
CP Email Invites | Mar. 8.22 | See TW Link
DT Celebration Invite with Ben Video | Mar. 11. 22 | Ben Video del. Feb. 25.22
Campus Ministry director Email | Mar. 15.22
Social | Date | TW Task Click Here
Invite Post | Mar. 21.22 | See TW Link
Night of Event Post | Mar. 23.22
Post Event- Join the Dreamteam/GT | Mar. 24. 22
WEB | REQ date Feb. 8 | TW Task Click Here
Wireframe | Feb. 16 | See TW Link
Update | Feb. 17.22
Ministry Edits | Feb. 17.22
Final | Mar. 9.22

## DTLaunch Products21
Dreamteam Launch Products 2021 | Date Requested | June.16.21 |  | TW task request | Click Here | Deadline | Aug. 18.21
Promo Products | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs
Email Graphic |  | Click Here | Jul 10.21 | 4 weeks | na | na | 600x400
2560x600
Web Graphics |  | Click Here | Jul. 15.21 | 4 weeks | na | na | 2560x600
600x400
QR Code Poster |  | Click Here | Jul. 14-Aug. 1.21 | 1 week | QTY=7 | 196 | 18x24 coraplast
HOT graphics |  |  |  |  | 1 per campus
1 Central
Invite Video |  | Click Here | Jul. 27.21 | 5 weeks | na | na
Event Products
Aframe |  | Click Here | Nov. 3.21 | Optional |  | $236ea | 24x36 coraplast
HOT Graphics
POP signs |  | Click Here | Sept. 1. 21 | Reused | 0 requested | 13 | 20x20 White 3mm PVC
CGS imaging |  |  |  |  | On hand Sept.2021
FN=2
OR=2
PB=2
ST=2
WT=2
W=2
QTY=12
Flag |  | Click Here | Option | 2 weeks | 0 requested | 135
CGS Imaging |  |  |  | CGS Imaging |  | 48 | 6.5’Staked flag (no hardware included)
Amazon |  |  |  | Amazon |  |  | Stake
Vinyl Floor Banner |  | Click Here | Oct. 14.21 | 12 weeks | 0 requested | 396 | 31x90 double sided
Displays2go |  |  |  |  | On hand Oct. 21
QTY=2
Check in Sign |  | Click Here | Nov. 11.21 | Resused | QTY=1-4 | 108 | Double sided
HOT Graphics |  |  |  |  | QTY=1-15 | 15 | 13mm scrim
Displays2go | [6 empty] | Hardware
[5 empty] | QTY=2 | 72 | 36x72SG
HOT Graphics | [6 empty] | 24x18 checkin
Photo Back drop |  | Click Here | Dec. 3. 2021 | Resused | On hand Dec. 21 | 308 | 120x96
CGS imaging |  |  |  |  | QTY=1
Swag |  | Click Here | Aug. 11.21 | 3-4 weeks | QTY=500 | 757
Wizard Pins |  |  |  |  | Adventure Pin
Gotprint |  |  |  |  | QTY=500 | 757
CedarCreek Pin
[5 empty] | QTY=1000 Cards | 25
[5 empty] | TOTAL= | 1539
Programming | Requested Feb. 6. 2022
Wow |  | TW link | June.15.21
Jul. 20.21
Pitch |  |  | No Notes
How |  |  | No notes

## DTLaunch Marketing21
Dreamteam Launch 2021Marketing | Date Requested | June. 16. 2021
Email-Event Aug. 18.21 | Dates | TW Task Click Here
Email #1: DT Segmented | Jul. 23. 21 | See TW Link
Email DT Actives | Jul. 13. 21
Email DT Actives | Jul. 27.21
Email#2 DT Segmented | Aug. 2.21
Email DT Actives | Aug. 10.21
Email #3 DT Segmented | Aug. 11. 22
Text | Aug. 15. 21
Email #4 Recap DT Segmented | Aug. 20.21
Social | Date | TW Task Click Here
1 Wk to DT Launch | Aug.11.21 | See TW Link
DT Launch | Aug. 18.21
Kelly's Story | Aug. 19.21
DT Launch Celebration | Aug. 22.21
WEB | Date | TW Task Click Here
Wireframe | Jul. 14.21 | See TW Link
Web Graphic delivered | Jul. 15. 21
Updated Wireframe | Jul 19.21
Updates | Jul.19.21
Ministry Updates | Jul. 19.21
Video delivered | Jul. 27.21
Final | Jul. 29.21