## ServeDay 2021 Products
Serve Day 2021 Products | Date Requested | May 18.2021 |  | TW task request | Click Here | Deadline | July 17.2021
Name | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs
Announcement Slide |  | HERE | June. 4. 21 | 1 week | na | 0 | 1920x1080
1080x1080
Web Graphics |  | HERE | June. 4.21 | 1 week | na | 0 | 2560x600
logo.png
600x400
APP Graphics |  | HERE | Used existing | 1 week | na | 0 | 1920x1080
1920x692
1024x1024
Social Media Graphics |  | HERE | Jun. 22.21 | 3 weeks | na | 0 | 1080x1080
1920x1080
Email Graphic |  | HERE | updated in 2022 | notused in 2021 | na | 0 | 600x156
Recap Video |  | HERE | Jul. 19.2021 |  | na | 0
Vision Video |  | HERE | May 10.21 |  | na | 0
Yard Signs |  | HERE | Jul. 2021 |  | 165 | 544 | 18x24 with 10x15 Hstake
imprint.com |  |  |  |  | FN=30
PB=60
OR=20
ST=20
WT=20
WH=15
T-Shirts |  | HERE | June. 18.2021 |  | QTY=1065 | 6095
Jupmode |  |  |  |  | credit | 3047
Findlay: Total Shirts -225
S -20
M -50
L -50
XL -50
2X – 40
3X – 15
South Toledo: Total Shirts - 135
S -25
M -25
L -30
XL -30
2X – 15
3X – 10
Whitehouse: Total Shirts - 145
S -30
M -40
L -30
XL -25
2X – 10
3X – 10
Oregon: Total Shirts - 85
S -10
M -20
L -20
XL -20
2X – 10
3X – 5
Overall total=590

## ServeDay 2022 Products
Serve Day 2022 Products | Date Requested | Apri. 14. 2022 |  | TW task request | Click Here | Deadline | July 23.2021
Name | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs
Announcement Slide | Need to build | HERE | NEED |  | na | 0 | 1920x1080
|  | Need to build |  |  |  |  | 1080x1080
Web Graphics |  | HERE | June.8.22 | 1 week | na | 0 | 2560x600
logo.png
600x400
APP Graphics |  | HERE | June 8.22 | 1 week | na | 0 | 1920x1080
1920x692
1024x1024
Social Media Graphics |  | HERE | NEED |  | na | 0 | 1080x1080
|  | Need to build |  |  |  |  | 1920x1080
Email Graphic |  | HERE | June 8. 2022 |  | na | 0 | 600x156
Recap Video | Built |  | NEED
Serve Day Vision Video | Built |  | NEED
Serve Day Kick off Slides | Built |  | NEED
Yard Signs |  | HERE | Jul. 7. 2022 |  | QTY=150 | 776 | 18x24 with 10x15 Hstake
imprint.com
T-Shirts |  | HERE | June 20.2022 |  | QTY=1065 | 5689
Jupmode |  |  |  |  | S=155
M=213
L=203
XL=158
2X=68
3X=23
4X=8
Overall total=828
Serve Day Tabernacle Shirt |  | June 2. 2022 | June 2. 2022 |  | M=10 | 475
L=10
XL=15
2X=15
Total=50

## ServeDay2021 Marketing
Serve Day Marketing | Date Requested | June 23. 21
Email | Dates | TW Task Click Here
Social | Date | TW Task Click Here
Story Register for project as a group | June. 24. 21 | HERE
Feature a group serving | Jul. 1. 21
Directory open Sign up. Story list projects | Jul. 3. 21
Story Directory project highlights | Jul. 8.21
Creative Serve day prompt Campus pastor to share | Jul. 9.21
Go live: Today's the Day. CP live serving | Jul.17.21
Recap Photography celebration | Jul. 18.21
Recap Video | Jul. 25.21
WEB | Date | TW Task Click Here
Change to Join a serve day project | June. 24.21 | HERE
Change to Serve on a Second Saturday | July 18. 21
Video Recap loaded the serve day web page | Oct. 15.21

## ServeDay 2022 Marketing
Serve Day Marketing | Date Requested | April 14. 2022
Email | Dates | TW Task Click Here
Social | Date | TW Task Click Here
WEB | Date | TW Task Click Here
Wireframe | June 15. 22 | HERE
Web Update | June 16.22
Ministry Edits | June 17.22
Web Update | June 17.22
Rock form | June 20.22
Webpage live | Jul7 2/3.22