## Women's Event 21Products
Womens Event | Date Requested | Aug. 11, 2021 |  | TW task request | Click Here | Deadline | Nov. 18, 2021
Promo Products | Image | Dropbox link | Date delivered | timeline | QTY | Price | Product Specs
Announcement slide |  | Click Here | Oct. 4. 21 | 8 weeks | 0 | 0 | 1920x1080
Email Graphic |  | Click Here | Oct.8.21 | 1 week | 0 | 0 | 600x156
1250x800
Social Media Graphic |  | Click Here | Oct. 4. 21 | 8 weeks | 0 | 0 | 1920x1080
1080x1080
Web Graphics |  | Click Here | Sept9-Nov.26.21 | 11 weeks | 0 | 0 | 2560x600
600x400
Invite Post Card |  | Click Here | Oct. 19.21 | 2 weeks | QTY=2500 | 86 | 4x6 14pt uncoated cover
Gotprint
Rock Banner |  | Click Here | Sept. 9.21 | 3 weeks | NA | 0
APP |  | Click Here | Oct. 8.21 | 1 week | NA |  | 1024x1024
1920x692
1920x1080
Videos |  | Click Here | Oct. 6. 21 | 4 weeks | Lauren Snyder Invite Video | 0
Invite Video |  |  | Nov.18.21 |  | Ben Post Event Video
Script Sept. 30.21
Post Event
Vision Dinner Slides |  | Click Here | Oct. 19.21 | 2 weeks | 16 Message Slides | 0 | 1920x1080
Event Products
Aframe (dated) |  | Optional |  | 4 weeks |  | 36ea | 24x36 coraplast
HOT Graphics
2x6 14pt uncoated cover
Swag-Scripture Cards + Holder |  | Click Here | Oct. 11-Nov. 16 | 4 weeks | Modlode Holders QTY=1000 | 2760
Modlode/Etsy |  |  |  |  | Gotprint Cards QTY=1000 | 290
Gotprint |  |  |  |  | 13 cards in a pack
Party Innovations |  |  |  |  | Party Innovations-Custom Ribbon | 184
3 Rolls
[5 empty] | Burlap Bags (Ministry purchase) | ??
POP signs |  | Optional |  | 2 weeks |  | $14 ea | 20x20 White 3mm PVC
CGS imaging
Flag | Optional | Click Here | Nov.8.21 | 2 weeks | Drinks | 128 ea | 6.5’ flag (no hardware included)
CGS Imaging |  |  |  | CGS Imaging | Free
[5 empty] | Food | $48 ea | Pole/Stake
Amazon |  |  |  | Amazon | Fun
Vinyl Floor Banner |  | Click Here | May .15.22 | 20 weeks | QTY=1 for Each Campus | 2374 | 31x90 double sided
($396 ea)
Displays2go
Photo Backdrop |  | Optional | NA | 2 weeks | QTY=1-4 | 308 | 120x96 Photo Display Fabric
CGS Imaging
QR Code Poster |  | Optional | Apr.29.21 | 2 weeks | PB=6 | 728
HOT |  |  |  |  | FN=4 | ($28 ea)
OR=4
ST=4
WH=4
WT=4
Total QTY=26
Check-in Central |  | Optional | NA | 2-3 weeks | On hand
HOT graphics |  |  |  |  | QTY=2 | 36 | 13mm Scrim
Displays2go |  |  |  |  | QTY=2 | 19 | Hardware
Event Apparel |  | Click Here | Nov.3.21 | 1 week | · Small: 28 | 2132 | 6010 Black
Tshirt |  |  |  |  | · Medium: 60 |  | Placement LC: 2"W FB: 8:"W
Jupmode |  |  |  |  | · Large: 44 |  | 313 Dark Teal
[5 empty] | · X Large: 44 |  | 310 Light Teal
· 2X Large: 16
· 3X Large: 8
· TOTAL=200
Programming
Comedian Message Slides |  |  | Nov. 15.21
Barb Roose Message Slides |  |  | Nov. 15.21
LED background |  |  | Nov. 11.21
Loop Slides |  |  | Nov.4.21
LC Video |  |  | Nov. 17.21
Wow |  |  | Sept. 20.21
How |  |  | No infor in TW
Program Pitch |  |  | Oct. 13.21
0

## Women's Event 21Marketing
Women's Event Marketing | Date Requested | Aug. 11.2021
Email | Dates | TW Task Click Here
Graphic | Oct. 8.21 | HERE
Email #1 Invite | Oct. 8.21
Confirmation Email #1 | Oct. 14.21
Email #2 Invite with Video | Oct. 19.21
Push Notification-Register | Nov. 3. 21
Text Cancelled almost full | Nov. 10.21
Confirmation Email#2 | Nov. 14.21
Hype Text | Nov. 17.21
Post Event
Post Event Text w Ben Video | Nov. 18. 21
Text Survey/Groups Link | Nov. 19.21
Womens Groups #1 Email | Nov. 26.21
Womens Groups #2 Email | Dec. 8. 21
Womens Groups #3 Email | Jan. 8.21
Social | Date | TW Task Click Here
Share Clip from Comedian/Register | Oct. 14.21 | HERE
Highlight from Womens group leader | Oct. 18.21
Womens group member quote/Register | Oct. 25.21
Flashback Mens event/Mens support | Oct. 28.21
Barb Preaching Clip/Event details | Nov. 3.21
Comedian Cliip | Nov. 4. 21
Respost from Barb/Register | Nov. 8.21
Respost from Barb/Few spots left | Nov. 10.21
Sold out | Nov. 12. 21
Event Reall on IG/Photo on FB | Nov. 18.21
Event Recap/Womens groups/Winter groups | Nov. 20-21
WEB | Date | TW Task Click Here
Wireframe w/headshot | Sept. 1. 21 | HERE
First Draft wo registeration link/video | Sept. 9.21
Guest speaker changed | Sept. 28.21
Edits | Sept. 29.21
Edits w/registration link | Sept. 30.21
Web update | Sept. 30.21
Web update | Oct. 4. 21
Edits | Oct. 4.21
Edits w. Registration deadline | Oct. 6. 21
Video ready for upload | Oct. 6. 21
Web update | Oct. 6. 21
Edit | Oct. 18. 21
Web update | Oct. 19.21
Edit | Nov. 12. 21
Web update | Nov. 12. 21
Edits Registration ends | Nov. 14.21
Edits Registration closed | Nov. 15.21
Page comes down | Nov. 26.21